## Simple Gantt Chart - BLANK
Project Plan
PROJECT TITLE | Digital Watch
DATE | 2023-02-08
TASK | TASK | Task | TASK | START | EXPECTED | DUE | DURATION | PCT OF TASK
ID | TITLE | Description | OWNER | DATE | END DATE | DATE | IN DAYS | COMPLETE
1 | CYRS Documentation | first creation | Rasha - Samuel | 2023-06-02 | 2023-07-02 | 2023-08-02 | 1 | 100%
2 | RTM Documentation | first creation | Abdallah - Youssef | 2023-06-02 | 2023-07-02 | 2023-08-02 | 1 | 100%
3 | HSI Documentation | first creation | Saher - Samira | 2023-06-02 | 2023-07-02 | 2023-08-02 | 1 | 100%
4 | CYRS Documentation | update CYRS according to its cross review | Rasha - Samuel | 14/2/2023 | 15/2/2023 | 15/2/2023 | 1 | 100%
5 | HSI Documentation | update HSI according to its cross review | Saher | 14/2/2023 | 15/2/2022 | 15/2/2023 | 1 | 100%
6 | SRS Documentation | first creation | Abdallah-Youssef-Samira | 14/2/2023 | 15/2/2023 | 15/2/2023 | 1 | 100%
7 | SRS Documentation | update SRS according to SQI document answer | Abdallah - Youssef - Samira | 16/2/2023 | 17/2/203 | 17/2/2023 | 1 | 100%
8 | SRS Documentation | update SRS according to its cross review | Samira Saeid | 2023-06-03 | 2023-07-03 | 17/3/2023 | 1 | 100%
9 | GDD Documentation | first creation | Abdullah - Yousef - Sameul - Samira - Rasha - Magraby | 2023-08-03 | 2023-11-03 | 17/3/2023 | 3 | 100%
10 | HSI Documentation | update HSI according to its cross review | Saher | 16/3/2023 | 17/3/2023 | 17/03/23 | 1 | 100%
11 | GDD Documentation | update GDD according to its cross review | Saher | 16/3/2023 | 17/03/2023 | 17/03/2023 | 1 | 100%
12 | CYRS Documentation | update CRS according to its cross review | Samuel | 16/3/2023 | 17/03/203 | 17/03/2023 | 1 | 100%
13 | CDD Documentation | first creation | Abdullah - Yousef - Sameul - Samira - Rasha - Magraby | 2023-12-03 | 17/03/2023 | 17/03/2023 | 5 | 100%